## Slide 1: HIGHER EDUCATION SUB-SECTOR 2021/22 PERFORMANCE REPORT Access, Equity, Quality, Relevance, Governance and Management
Directorate of Higher Education, 9th November, 2022, BICC
Ministry of Education
MINISTRY OF EDUCATION

## Slide 2
Brief on HEIs and
Strategic Objectives
Major Achievements
Major Challenges
Next Steps
OUTLINE
Progress on NESIP & MIP-1 Targets
Cross-cutting Issues
General Objective: Ensure access and equity, quality and relevance and effective and efficient governance and management of the Higher Education subsector.
2021/22 Achievements vs Targets
Ministry of Education

## Slide 3
Ministry of Education
Higher education institutions & STAKEHOLDERS
Other Key Stakeholders
NCHE
HESLGB
DODeL
DSTI
NCST
APUMA
MAREN
In the year under review, the National Council for Higher Education (NCHE) reported a total of fifty four (54) HEIs as:
HEIs
Public HEIs (21);
Private HEIs (30);
Professional HEIs (1) and
Tuition Providing HEIs (2)
NCHE also recognized eight (8) Colleges regulated by the Nurses and Midwives Council of Malawi and the Medical Council of Malawi as duly registered HEIs

## Slide 4
Ministry of Education
Higher Education Sub-Sector STRATEGIC Objectives
Strategic Objectives
Increase equitable access for students in Higher Education.
Improve skills, quality and relevance of Higher Education for industry or market Priority Actions
Establish an efficient and effective governance and management system.
General Objective:
Ensure access and equity, quality and relevance and effective and efficient governance and management of the Higher Education subsector.

## Slide 5
Ministry of Education
NESIP INDICATORS AND 2022 ACHIEVEMENTS VS 2025 TARGETS
Outcome 1:
Increased equitable access for students in Higher Education
INDICATOR NAME | BASELINE 2019 | 2021/2022 ACHIEVEMENTS | 2025 TARGETS
Total University Enrolment (public and private) | 30,970 | 56,624 (of which 17% are ODeL) | 45,500
Gender Parity Index (for enrolment in public universities) | 0.5 | 0.63 | 0. 8
Total number of students offered loans | 13,035 | 20,786 | 17,065
Number of institutions with special needs facilities | 1 | 3 (total number during year under review = 112) | 10

## Slide 6
Ministry of Education
NESIP & MIP-1 INDICATORS AND 2022 ACHIEVEMENTS VS 2025 TARGETS
Outcome 2:
Improved skills, quality and relevance of Higher Education for industry or market
INDICATOR NAME | BASELINE 2019 | 2021/2022 ACHIEVEMENTS | 2025 TARGETS
Percentage of accredited institutions of higher learning with quality assurance mechanism | 20% | 54% | 70%
Percentage of Lecturers with PhDs | 30% (Min) | 35% (M =25%; F = 10%) (public HEIs) | 40%
Number of business innovation and technological incubation centres (fabrication laboratories, maker spaces, innovation hubs, innovation garages and technology parks) established | 0 | 5 (MUST-Industrial park; Mzuni- ICT Incubation Centre, and Tourism and Hospitality Business Centre; LUANAR – Agri-Hub; MUBAS- Innovation Hub; KUHeS- Innovation Centre) | 9
Establish Malawi Academy of Sciences (MAS) | 0 | 1 (established and launched; awaiting registration) | 1
Re-establish national research fund | 0 | 1(S&T fund operationalized under NCST but lacks adequate financing which was at MK291million for 2021/22) | 1

## Slide 7
Ministry of Education
NESIP INDICATORS AND 2022 ACHIEVEMENTS VS 2025 TARGETS
Outcome 3:
Efficient and effective governance and management system established
INDICATOR NAME | BASELINE 2019 | 2022 ACHIEVEMENTS | 2025 TARGETS
Number of operationalized newly established universities that were delinked from UNIMA; | 0 | 3 (VCs positions filled in all, 2 DVCs in place. Other senior positions yet to be filled) | -
% of Higher Education institutions aligned to the NQF | 0% | 0% (However, MAQA bill is currently undergoing legal review; and NQF is under development led by DQAS targeting April, 2023) | 50%
Higher Education overarching Bill in place | 0 | HEOB is currently under legal review targeting April 2023 | 1

## Slide 8
Ministry of Education
CROSS-CUTTING ISSUES: ACHIEVEMENTS
Established online big data center through High Performance Computing (HPC) hosted at the National Data Center (NDC) managed by Malawi Research and Education Network;
National Inclusive Education Policy under development
A model gender and anti-sexual harassment policy for Higher Education in Malawi was developed in June, 2021
An HIV and AIDS Strategy for Higher Education Institutions was developed by NCHE in collaboration with NAC
A number public universities are in the process of establishing holding companies (e.g @MUBAS and LUANAR; while MUST has a vibrant Endowment Fund; MZUNI, a Trust Fund); As of 2020/230, self-generated resources were at an average of 30%.
MUST has consistently held Girls Science Camps for Secondary Schools
ICT
Inclusive Edu.
Gender
HIV/AIDS
Resource Mobilization
Girls Camps

## Slide 9
Ministry of Education
TOWARDS ACHIEVEMENT OF NESIP AND MIP-1 TARGETS
Targets
Achieved?
Not Achieved?
Why?
Outcome/Issue | Status/Comment
Increased University Enrolment (public and private) | Target surpassed, thanks to: Provision of loans and scholarships to needy, vulnerable and deserving students; expansion and introduction of ODeL programmes in universities expansion of infrastructure; and increased private sector participation.
Gender Parity | On course, though training at 0.63 vs for 2022 target of 0.7
Total number of student offered loans | Target surpassed due to Government commitment to increased funding for loans
Alignment of HEIs to NQF | Behind Schedule. Delays in finalization of NQF means that HEIs cannot yet be aligned. Target is April 2023.
Finalization of Higher Education overarching Bill | Behind Schedule. Funding had been an issue but now funded from 2022/2023 FY under SAVE project. Target is April 2023.

## Slide 10
Ministry of Education
MAJOR ACHIEVEMENTS
All public universities & five private ones have been connected to 24/7 internet campus Wi-Fi including in hostels for some institutions through MAREN;
Expansion of DCE with support from JICA;
Delinked universities fully operationalized
Public universities selection jumped from 6,941 to 7,439 and for the first time ever achieved a Male: Female ratio of 52:48;
Consultations on Selection Policy commenced;
Hostel at KUHeS-LL constructed under PPP arrangement;
Construction projects underway at all public universities through PSIP, PPPC and DPs support;
University students’ loan disbursed to 20,786 against a target of 15,050;
Increased number of ODeL students at 10,245;
Funding for students’ loans including for ODeL students, secured under SAVE project;
Skills needs assessment initiated- as at October 2022, report awaiting validation and submission to, and approval by relevant authorities;
Application process for new Centres of Excellence initiated – 6 awarded in 2022.
Notable 2021/22 Achievements

## Slide 11
Ministry of Education
MAJOR CHALLENGES & MITIGATION
HEMIS development and integration with EMIS is underway with funding from SAVE and is being prioritized;
Continuous engagement with PPDA;
Support towards PPP arrangement for construction of students’ hostels.
Continued lobbying Treasury for special funding for Research modelled on NRF of RSA or NSF of USA.
CHALLENGES
Higher Education data not conveniently organized
Construction projects facing challenges with PPDA and inadequate funding
Limited campus accommodation with connectivity available only on campus
Funding for Research

## Slide 12
Ministry of Education
NEXT STEPS
    To prioritize:
    HEMIS and integration with EMIS;
    NQF;
    Support for PPP arrangements for students’ accommodation construction;
    Finalization of Higher Education Overarching Bill;
    Finalization of selection policy to enhance transparence and accountability.
2022/23 Prioritized Interventions

## Slide 13
THANK YOU FOR YOUR ATTENTION
Ministry of Education